## QNIDS Tracker
⬡ QNIDS Project Todo Tracker — 2 Months · 2 Persons
✅ Checkbox column (A) mein ✓ likh do jab task ho jaye ¦ Person: A = Backend/ML B = GUI/Frontend AB = Dono ¦ Difficulty: Easy Medium Hard
✓ Done | Who | Task | Level | Days | Auto Status
MONTH 1 — Data · ML · QPSO · Anomaly Detection
WEEK 1 — Setup, Dataset & Basic GUI ¦ Day 1–7
| A | Python environment setup karo — VS Code, virtual environment banao | Easy | Day 1–2
| A | Libraries install: scikit-learn, pandas, numpy, deap, pyswarm, scapy, matplotlib, PyQt5 | Easy | Day 1–2
| A | NSL-KDD dataset download karo — unb.ca/cic/datasets/nsl.html | Easy | Day 1–2
| B | PyQt5 install — basic 'Hello World' window banao — sirf test | Easy | Day 1–2
| B | GitHub repository banao — dono ka access do — README likho | Easy | Day 1–2
| B | GUI ka sketch banao paper pe — layout, sidebar, table, metric cards | Easy | Day 1–2
| A | NSL-KDD explore karo — rows, columns, attack types, distribution dekho | Easy | Day 3–4
| A | Null values check karo — df.isnull().sum() run karo | Easy | Day 3–4
| A | Attack type bar chart banao — kitne Normal, DoS, DDoS etc | Easy | Day 3–4
| B | PyQt5 mein main window banao — dark theme (#0a0f1a background) | Easy | Day 3–4
| B | Layout: left sidebar + main content + right panel — placeholder boxes | Medium | Day 3–4
| A | Label encoding — attack types ko numbers mein convert karo | Easy | Day 5–7
| A | Min-Max Normalization apply karo — MinMaxScaler use karo | Easy | Day 5–7
| A | 80/20 stratified train-test split — train.csv aur test.csv save karo | Easy | Day 5–7
| B | 4 metric cards banao: Accuracy, FPR, Attacks Detected, Packets Analyzed | Medium | Day 5–7
| B | Live feed table banao — columns: Time, IP, Attack Type, Verdict, Confidence | Medium | Day 5–7
| B | GitHub pe push — commit: 'Week 1 complete' | Easy | Day 5–7
WEEK 2 — Classical ML Baseline + GUI Tables ¦ Day 8–14
| A | Random Forest train karo — 41 features, n_estimators=100 | Easy | Day 8–10
| A | RF accuracy, precision, recall, F1, FPR nikalo — classification_report | Easy | Day 8–10
| A | Decision Tree train karo — criterion='gini', max_depth=10 | Easy | Day 8–10
| A | DT ke bhi same metrics nikalo aur save karo | Easy | Day 8–10
| B | Table mein dummy rows add karo — test karo ke sahi dikh rahi hain | Easy | Day 8–10
| B | Row colors: Normal=green, Attack=red, Unknown=orange | Medium | Day 8–10
| A | Confusion matrix banao — RF ke liye — seaborn heatmap | Easy | Day 11–12
| A | Dono models results results_baseline.txt mein save karo | Easy | Day 11–12
| A | Person B ko results table de do — GUI mein dikhane ke liye | Easy | Day 11–12
| B | Sidebar: Dashboard, Live Detection, QPSO Analysis, Reports links | Medium | Day 11–12
| B | Metric cards mein baseline numbers daalo — static for now | Easy | Day 11–12
| A | Trained models save karo — rf_model.pkl, dt_model.pkl | Easy | Day 13–14
| B | GUI screenshot lo — GitHub push karo | Easy | Day 13–14
| AB | Dono milke: Week 2 review karo — kya bana, kya bacha | Easy | Day 13–14
WEEK 3 — QPSO Implementation + Live/Demo Toggle ¦ Day 15–21
| A | PSO concept samjho — YouTube: 'PSO feature selection python tutorial' | Medium | Day 15–17
| A | DEAP library basic example run karo — documentation padho | Medium | Day 15–17
| A | Basic PSO feature selection likho — binary (1=selected, 0=not) | Hard | Day 15–17
| B | Scapy install — basic packet capture test — console pe print karo | Medium | Day 15–17
| B | Live Mode toggle button banao — blue, top right mein | Medium | Day 15–17
| B | Demo Mode button — red — CSV file select dialog khule | Medium | Day 15–17
| A | QPSO quantum position update formula add karo | Hard | Day 18–19
| A | Fitness function: RF accuracy as fitness — zyada accuracy = better | Medium | Day 18–19
| A | QPSO run karo — 41 se best ~19 features select karo | Hard | Day 18–19
| B | Live Mode ON: real packets table mein — IP, Protocol, Size sirf | Medium | Day 18–19
| B | Demo Mode: CSV row by row 0.5sec mein table update karo | Medium | Day 18–19
| A | QPSO selected 19 features pe RF dobara train karo | Easy | Day 20–21
| A | Compare: 41 features RF vs 19 features RF — accuracy better? | Easy | Day 20–21
| A | Selected features list save karo — qpso_features.txt | Easy | Day 20–21
| A | New model save karo — rf_qpso_model.pkl | Easy | Day 20–21
| B | Demo Mode mein Pause/Resume button add karo | Easy | Day 20–21
| B | Speed slider: Slow / Normal / Fast simulation speed | Medium | Day 20–21
| B | GitHub push — commit: 'Week 3 QPSO + toggle complete' | Easy | Day 20–21
WEEK 4 — Anomaly Detection + Model Connect ¦ Day 22–28
| A | Isolation Forest samjho — sklearn docs padho — 10 min kaafi | Easy | Day 22–23
| A | Sirf normal traffic pe Isolation Forest train karo — contamination=0.05 | Easy | Day 22–23
| A | Model save karo — anomaly_model.pkl | Easy | Day 22–23
| B | Alert popup banao — Unknown Threat pe orange warning dialog | Medium | Day 22–23
| B | Sound alert add karo — system beep — attack pe bajey | Easy | Day 22–23
| A | Known attacks pe test: detection rate nikalo | Easy | Day 24–25
| A | Normal traffic pe test: false positive rate nikalo | Easy | Day 24–25
| A | Unknown attack test: U2R training se hata ke test karo | Medium | Day 24–25
| B | Matplotlib pie chart embed karo PyQt5 mein — attack distribution | Medium | Day 24–25
| B | Right panel: QPSO selected 19 features importance bars show karo | Medium | Day 24–25
| A | QPSO+RF + Anomaly detection ek predict() function mein combine karo | Medium | Day 26–28
| B | Demo Mode mein Person A ka combined model connect karo | Hard | Day 26–28
| AB | End to end test: CSV load → predict → GUI mein show | Medium | Day 26–28
| B | Metric cards ab real numbers show karen — dummy data hata do | Medium | Day 26–28
| AB | GitHub push — commit: 'Month 1 Complete 🎉' | Easy | Day 26–28
MONTH 2 — Integration · Polish · Testing · Presentation
WEEK 5 — Full Integration + UNSW-NB15 ¦ Day 29–35
| A | UNSW-NB15 dataset download karo — research.unsw.edu.au | Easy | Day 29–31
| A | UNSW-NB15 pe same preprocessing pipeline reuse karo | Medium | Day 29–31
| A | QPSO+RF model UNSW-NB15 pe bhi train karo — results save karo | Medium | Day 29–31
| B | GUI mein dataset dropdown: NSL-KDD / UNSW-NB15 | Easy | Day 29–31
| B | Live Mode properly connect karo Scapy se — basic info table mein | Hard | Day 29–31
| A | Dono datasets ke final results ek table mein — thesis ke liye | Easy | Day 32–35
| B | Dataset switch pe GUI update ho — models reload hon | Medium | Day 32–35
| AB | Full integration test — dono datasets pe poora demo chalao | Medium | Day 32–35
WEEK 6 — Polish + Export + Final Charts ¦ Day 36–42
| A | Final evaluation table: Classical RF vs QPSO+RF — sab metrics | Easy | Day 36–38
| A | Confusion matrix PNG save karo — thesis ke liye | Easy | Day 36–38
| A | Feature importance bar chart banao — 19 QPSO features ka | Easy | Day 36–38
| A | QPSO convergence curve plot banao — iterations vs fitness | Medium | Day 36–38
| B | PDF Export button — fpdf ya reportlab library | Medium | Day 36–38
| B | CSV Export button — current session ka data | Easy | Day 36–38
| B | GUI fonts, colors, spacing poori app mein consistent karo | Medium | Day 39–42
| B | Loading screen add karo — models load hote waqt | Easy | Day 39–42
| B | About section: project name, team, supervisor, session | Easy | Day 39–42
| B | App icon (.ico) banao aur set karo | Easy | Day 39–42
| A | Sab charts aur plots GUI mein embed karo | Medium | Day 39–42
WEEK 7 — Testing + Bug Fixing + Docs ¦ Day 43–49
| A | Edge case test: empty CSV load karo — crash nahi hona chahiye | Medium | Day 43–45
| A | Wrong format file load karo — graceful error message aaye | Medium | Day 43–45
| A | Code mein comments add karo — har function explain karo | Easy | Day 43–45
| A | requirements.txt banao — pip freeze > requirements.txt | Easy | Day 43–45
| B | Dost ke laptop pe install karke test karo — sab kaam karta? | Medium | Day 43–45
| B | Crashes / freeze list banao aur fix karo | Medium | Day 43–45
| B | GUI responsive check — window resize pe elements sahi rahein | Easy | Day 43–45
| B | User guide PDF banao — screenshots ke saath — install + use | Medium | Day 46–49
| A | GitHub README update: description, screenshots, install steps | Easy | Day 46–49
| B | Demo video record karo — 2-3 min screen recording | Easy | Day 46–49
| AB | Final bug list banao — sab fix karo — koi known issue na rahe | Medium | Day 46–49
WEEK 8 — Final Prep + Presentation + Practice ¦ Day 50–56
| A | Thesis ke liye results organize karo — tables, graphs sab ek jagah | Easy | Day 50–52
| A | Presentation slides mein actual results update karo | Easy | Day 50–52
| A | Defense questions ke answers dobara padho aur yaad karo | Easy | Day 50–52
| B | Final GUI screenshots lo — high quality — slides ke liye | Easy | Day 50–52
| B | App cleanly package karo — models + code + data ek folder mein | Easy | Day 50–52
| B | Slides mein GUI screenshots add karo | Easy | Day 50–52
| AB | Live demo 3 baar practice: open→live→demo→unknown alert→export | Easy | Day 53–56
| B | Backup plan: agar live fail ho → screen recording ready rakho | Easy | Day 53–56
| A | Poori presentation ek baar rehearse karo — timing check karo | Easy | Day 53–56
| AB | Final GitHub push — sab code clean, commented, working | Easy | Day 53–56
| AB | 🎉 PROJECT COMPLETE — Dono celebrate karo! | Easy | Day 53–56